## Launch Hardening
ID | Priority | Category | Task | Description | Acceptance Criteria | Status | Implementation Notes | Files Modified | Commit Hash | Test Results
RB-001 | P0 | Finance | Currency Flow | Persist currency through Cart/Order/Payment. | Currency-safe checkout | Completed | Currency snapshots persist through cart, order, item and payment; mixed carts rejected; gateway sends IRR/IRT. | V0006; Cart/Checkout/Payment services; DTOs/entities | f663ea1 | Release build; 396 unit; Commerce integration 5/5
RB-002 | P0 | Finance | Paid Cancellation | Refund or block paid cancellations. | Financial integrity | Completed | Paid orders are blocked from ordinary cancellation and must use the idempotent refund workflow. | OrderService; OrderLifecycleHardeningTests | 39024e2 | Release build; 396 unit
RB-003 | P0 | Security | Dependencies | Upgrade vulnerable packages. | No vulnerabilities | Completed | Upgraded HtmlSanitizer and pinned System.Text.Json 8.0.5; advisory scan is clean. | Vitorize.Infrastructure.csproj | 39024e2 | dotnet list package --vulnerable: clean
RB-004 | P0 | Database | DACPAC Approval | Finalize schema artifact. | Approved release | Blocked - External Dependency | Added clean-publish, existing-upgrade, checksum, pre/post validation, recovery, and DBA/release sign-off rehearsal pack. DBA approval and production-like execution remain required. | Database/Rehearsal; Database/Tests/Test-DatabaseDeploymentAssets.ps1 | 9aaf875 | Deployment asset test passed; Commerce SQL integration previously passed 5/5
RB-005 | P0 | Payments | Production Gateway | Validate Zarinpal production. | Live payment verified | Blocked - External Dependency | One validated DB-backed sandbox/live model; Production startup rejects incomplete, sandbox, invalid merchant, callback, and public-origin configurations. Certification runbook added. | ZarinpalPaymentConfiguration; ZarinpalGatewayService; ZARINPAL-PRODUCTION-CERTIFICATION-RUNBOOK.md | 8c14d14 | Release build; 12 focused configuration/fault tests passed
RB-006 | P0 | Operations | Backup & Restore | Automated backup and restore drill. | Recovery verified | Blocked - External Dependency | Added safe SQL backup/VERIFYONLY, isolated restore/DBCC, public/private media manifest, retention/RPO/RTO and operator sign-off pack. Live restore drill remains required. | ops/backup | bb0b0a1 | All backup PowerShell scripts parsed successfully
RB-007 | P0 | Hosting | Production Hosting | DataProtection, proxy, shared media. | Restart/multi-node pass | Blocked - External Dependency | API/Web persist shared Data Protection keys, trust configured proxies, validate writable durable public/private roots, and document sticky-session/rolling restart rehearsal. | HostingRuntimeOptions; API/Web Program; PRODUCTION-HOSTING-RUNBOOK.md | 1e41c1d | Release build; 400 unit; ApiSecurity SQL integration 17/17
REQ-001 | P1 | Auth | Refresh Tokens | Auto refresh and revoke logout. | Session lifecycle | Completed | Scheme-matched logout revocation; automatic single-flight refresh; one GET/HEAD retry only; unsafe mutations never replay; failed refresh clears only its local scheme and returns through a safe login cleanup endpoint. Tokens are not logged. | Vitorize.Web/Endpoints/AdminAuthEndpoints.cs; CustomerAuthEndpoints.cs; AuthSessionEndpoints.cs; ApiClient.cs; SessionTokenRefreshCoordinator.cs; AccessTokenProvider.cs; auth tests | c712e99, 4a26105, 74399dc | Release build 0 warnings; unit 409/409; integration 113/113; Playwright auth 36/36
REQ-002 | P1 | Admin | Refund UI | Refund/Reconcile screens. | Finance UI complete | Completed | Admin payment details expose refund eligibility, reason/method input, persisted refund/audit history, manual gateway completion, wallet refunds, and reconciliation. FinanceManage protects money-moving actions; server locks and idempotency prevent duplicates. | AdminPaymentsController; PaymentsController; PaymentService; AdminPaymentReadService; Admin Payments UI; finance integration tests | bc43474, 928bb81 | Release build; unit 409/409; integration 114/114; Admin Playwright 7/7
REQ-003 | P1 | Orders | Completion Rules | Prevent premature completion. | Workflow correct | Completed | Manual/support orders cannot be marked complete until every item is delivered. | OrderService; OrderLifecycleHardeningTests | 39024e2 | Release build; 396 unit
REQ-004 | P1 | Support | Generic Ticket | Remove GTA VI hardcode. | Dynamic subject | Completed | Automatic support subjects now use the actual product title and order number rather than GTA VI. | PaymentService | 39024e2 | Focused Commerce/SQL integration remains green
REQ-005 | P1 | Support | Ticket Semantics | Handle multi-item support. | Support tests | Completed | Exactly one automatic fulfilment ticket is created per qualifying order, with every SupportRequired OrderItem linked to it. Customer-created order tickets stay separate. A filtered unique database index, payment idempotency, and safe retry preserve the invariant under replay and concurrency. | V0007; Ticket/OrderItem model; DbContext; PaymentService; TicketService; ticket DTOs and Admin/Customer ticket UI; support integration and Playwright tests | ffa9658, 058148f, 24a149f, aed83ff | Release build 0 warnings; unit 410/410; SQL integration 117/117; focused browser Customer/Admin support flow 1/1 (57.1s); clean migration + upgrade rehearsal verified
REQ-006 | P1 | Catalog | Server Filters | Move filters server-side. | Correct counts | Completed | Storefront paging, counts, product type, delivery, verification, price, availability, and discount-tier filters now execute in the public catalog query. Invalid price ranges and discount thresholds are rejected server-side; the UI only owns filter state. | ProductFilterDto; ProductService; ShopBrowser; catalog unit and SQL integration tests | 9f885dc | Release build 0 warnings; focused unit 3/3; SQL-backed catalog API integration 1/1; storefront Playwright 1/1
REQ-007 | P1 | QA | Visual Stability | Fix nondeterministic visuals. | All visual tests pass | In Progress | Recent visual-baseline fixes exist; all-project visual regression must be rerun before completion. | tests/Vitorize.E2E |  | Not rerun in this milestone
REQ-008 | P1 | CI/CD | Pipeline | Automated release gate. | CI green | Not Started | No checked-in CI workflow was found. |  |  | Repository inspection
REQ-009 | P1 | Health | Health Checks | Readiness/liveness. | Operational health | Not Started | Health endpoint exists but distinct liveness/readiness probes are not implemented. |  |  | Repository inspection
REQ-010 | P1 | Admin | Server Paging | Replace client paging. | Scalable admin | Not Started | Several admin screens still load unbounded lists or use client paging. |  |  | Repository inspection
REQ-011 | P2 | Security | 2FA | 2FA, email verify, devices. | Security complete | Not Started | OTP support exists; 2FA, email verification, and device/session management remain open. |  |  | Repository inspection
REQ-012 | P2 | Privacy | Addresses | Addresses and privacy flows. | Customer complete | Not Started | UserAddresses persistence exists but customer address and privacy workflows are absent. |  |  | Repository inspection
REQ-013 | P2 | Checkout | Legal | Terms/refund acknowledgement. | Legal compliance | Not Started | Checkout acknowledgement and legal disclosure workflow are absent. |  |  | Repository inspection
REQ-014 | P2 | Support | Assignment | SLA and assignment. | Support ops | Not Started | Ticket queue exists; assignment and SLA controls are absent. |  |  | Repository inspection
REQ-015 | P2 | Catalog | Free Products | Support or block free checkout. | Consistent behavior | Completed | Free checkout is explicitly blocked before order creation or inventory reservation. | CheckoutService; CommerceIntegrationTests | 39024e2, 5ffe2f2 | Commerce integration 5/5